PMBOK (version 6)

Document version 20171114 001

Process Inputs and Outputs

Contents

Integration Initiating Process – Develop Project Charter #4.1	3

Integration Planning Process – Develop Project Management Plan #4.2	5

Integration Execution Process – Direct and Manage Project Work #4.3	7

Integration Execution Process – Manage Project Knowledge #4.4	10

Integration Monitor & Control  Process – Monitor & Control  Project Work #4.5	13

Integration Monitor & Control  Process – Perform Integrated Change Control #4.6	17

Integration Closing Process – Close Project or Phase #4.7	20

Scope Planning Process – Plan Scope Management #5.1	24

Scope Planning Process – Collect Requirements #5.2	27

Scope Planning Process – Define Scope #5.3	30

Scope Planning Process – Create WBS #5.4	32

Scope Planning Process – Validate Scope #5.5	34

Scope Monitor & Control  Process – Control Scope #5.6	37

Schedule Planning Process – Plan Schedule Management #6.1	40

Schedule Planning Process – Define Activities #6.2	42

Schedule Planning Process – Sequence Activities #6.3	44

Schedule Planning Process – Estimate Activity Durations #6.4	46

Schedule Planning Process – Develop Schedule #6.5	49

Schedule Controlling Process – Control Schedule #6.6	54

Cost Planning Process – Plan Cost Management #7.1	57

Cost Planning Process – Estimate Costs #7.2	59

Cost Planning Process – Determine Budget #7.3	62

Cost Monitor & Control  Process – Control Costs #7.4	66

Quality Planning Process – Plan Quality Management #8.1	69

Quality Planning Process – Manage Quality #8.2	71

Quality Monitor & Control  Process – Control Quality #8.3	73

Resource Planning Process – Plan Resource Management #9.1	75

Resource Planning Process – Estimate Activity Resources #9.2	76

Resource Execution Process – Acquire Resources #9.3	78

Resource Execution Process – Develop Team #9.4	80

Resource Execution Process – Manage Team #9.5	82

Resource Monitor & Control  Process – Control Resources #9.6	84

Communication Planning Process – Plan Communications Management #10.1	87

Communication Execution Process – Manage Communications #10.2	90

Communication Monitor & Control  Process – Monitor Communications #10.3	92

Risk Planning Process – Plan Risk Management #11.1	93

Risk Planning Process – Identify Risks #11.2	95

Risk Planning Process –Perform Qualitative Risk Analysis #11.3	97

Risk Planning Process –Perform Quantitative Risk Analysis #11.4	99

Risk Planning Process –Plan Risk Responses #11.5	101

Risk Execution Process – Implement Risk Responses #11.6	103

Risk Monitor & Control  Process – Monitor Risks #11.7	104

Procurement Planning Process – Plan Procurement Management #12.1	106

Procurement Execution Process – Conduct Procurements #12.2	109

Procurement Monitor & Control  Process – Control Procurements #12.3	112

Stakeholder Initiating Process – Identify Stakeholders #13.1	114

Stakeholder Planning Process – Plan Stakeholder Engagement #13.2	115

Stakeholder Execution Process – Manage Stakeholder Engagement #13.3	116

Stakeholder Monitor & Control  Process – Monitor Stakeholder Engagement #13.4	117

| Integration Initiating Process – Develop Project Charter #4.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Develop Project Charter | .1 Business documents: - Business Case - Benefits Management Plan | .1 Expert judgment |  | .1 Project charter | Project Integration Management |
|  | .2 Agreements | .2 Data gathering - Brainstorming - Focus groups - Interviews |  | .2 Assumption log |  |
|  | .3 Enterprise environmental factors | .3 Interpersonal and team skills - Conflict management - Facilitation - Meeting management |  |  |  |
|  | .4 Organizational process assets | .4 Meetings |  |  |  |

| Integration Planning Process – Develop Project Management Plan #4.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Develop Project Management Plan | .1 Project charter | .1 Expert judgment |  | .1 Project management plan | Project Integration Management |
|  | .2 Outputs from other processes | .2 Data gathering - Brainstorming - Checklists - Focus groups - Interviews |  |  |  |
|  | .3 Enterprise environmental factors | .3 Interpersonal and team skills - Conflict management - Facilitation - Meeting management |  |  |  |
|  | .4 Organizational process assets | .4 Meetings |  |  |  |

| Integration Execution Process – Direct and Manage Project Work #4.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Direct and Manage Project Work | .1 Project management plan - Any component | .1 Expert judgment |  | .1 Deliverables | Project Integration Management |
|  | .2 Project documents - Change log - Lessons learned register - Milestone list - Project schedule - Requirements traceability matrix - Risk register - Risk report - (* “Issues are Risks happening”) | .2 Project management information system - (* It is a challenge to get out of Capability Maturity Level 1 Heroic and into Capability Maturity Level 2, unless you have a PMIS) |  | .2 Work performance data |  |
|  | .3 Approved change requests | .3 Meetings |  | .3 Issue log - (* “Issues are Risks happening”) |  |
|  | .4 Enterprise environmental factors |  |  | .4 Change requests |  |
|  | .5 Organizational process assets |  |  | .5 Project management plan updates |  |
|  |  |  |  | .6 Project document updates - Activity list - Assumption log - Lessons learned register - Requirements documentation - Risk Register - Stakeholder register |  |
|  |  |  |  | .7 Organizational process assets updates |  |
| (* This is an idea from PRINCE2.) |  |  |  |  |  |

| Integration Execution Process – Manage Project Knowledge #4.4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Manage Project Knowledge | .1 Project management plan - All components | .1 Expert judgment |  | .1 Lessons learned register | Project Integration Management |
|  | .2 Project documents - Lessons learned register - Project team assignments - Resource breakdown structure - Source selection criteria - Stakeholder register | .2 Knowledge management |  | .2 Project management plan updates - Any component |  |
|  | .3 Deliverables | .3 Information management |  | .3 Organizational process assets updates |  |
|  | .4 Enterprise environmental factors | 4. Interpersonal and team skills - Active listening - Leadership - Networking - Political awareness |  |  |  |
|  | .5 Organizational process assets |  |  |  |  |

| Integration Monitor & Control Process – Monitor & Control Project Work #4.5 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Monitor & Control Project Work | .1 Project management plan - Any component | .1 Expert judgment |  | .1 Work performance reports | Project Integration Management |
|  | .2 Project documents - Assumption log - Basis of estimates - Cost forecasts - Issue log - Lessons learned register - Milestone list - Quality reports - Risk register - Risk report - Schedule forecasts | .2 Data analysis - Alternative analysis - Cost-benefit analysis - Earned value analysis - Root cause analysis - Trend analysis - Variance analysis |  | .2 Change requests |  |
|  | .3 Work performance information | .3 Decision making |  | .3 Project management plan updates - Any component |  |
|  | .4 Agreements | 4. Meetings |  | .4 Project documents updates - Cost forecasts - Issue log - Lessons learned register - Risk register - Schedule forecasts |  |
|  | .5 Enterprise environmental factors |  |  |  |  |
|  | .6 Organizational process assets |  |  |  |  |

| Integration Monitor & Control Process – Perform Integrated Change Control #4.6 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Perform Integrated Change Control | .1 Project management plan - Change management plan - Configuration management plan - Scope baseline - Cost baseline | .1 Expert judgment |  | .1 Approved change requests | Project Integration Management |
|  | .2 Project documents - Basis of estimates - Requirements traceability matrix - Risk report | .2 Change control tools |  | .2 Project management plan updates - Any component |  |
|  | .3 Work performance reports | .3 Data analysis - Alternatives analysis - Cost-benefit analysis |  | .3 Project document updates - Change log |  |
|  | .4 Change requests | 4. Decision making - Voting - Autocratic decision making - Multicriteria decision analysis |  |  |  |
|  | .5 Enterprise environmental factors | .5 Meetings |  |  |  |
|  | .6 Organizational process assets |  |  |  |  |

| Integration Closing Process – Close Project or Phase #4.7 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL |  | CLOSING |
| Process name | Inputs | Tools and techniques |  | Outputs | Knowledge Area |
| Close Project or Phase | .1 Project charter | .1 Expert judgment |  | .1 Project documents updates - Lessons learned register | Project Integration Management |
|  | .2 Project management plan - All components | .2 Data analysis - Document analysis - Regression analysis - Trend analysis - Variance analysis |  | .2 Final product, service, or result transition |  |
|  | .3 Project documents - Assumption log - Basis of estimates - Change log - Issue log - Lessons learned register - Milestone list - Project communications - Quality control measurements - Quality reports - Requirements documentation - Risk register - Risk report | .3 Meetings |  | .3 Final report |  |
|  | .4 Accepted deliverables |  |  | .4 Organizational process assets updates |  |
|  | .5 Business documents - Business case - Benefits management plan |  |  |  |  |
|  | .6 Agreements |  |  |  |  |
|  | .7 Procurement documentation |  |  |  |  |
|  | .8 Organizational process assets |  |  |  |  |

| Scope Planning Process – Plan Scope Management #5.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Scope Management | .1 Project charter | .1 Expert judgment | .1 Scope management plan | Project Scope Management |
|  | .2 Project management plan - Quality management plan - Project life cycle description - Development approach | .2 Data analysis - Alternative analysis | .2 Requirements management plan |  |
|  | .3 Enterprise environmental factors | .3 Meetings |  |  |
|  | .4 Organizational process assets |  |  |  |

| Scope Planning Process – Collect Requirements #5.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Collect Requirements | .1 Project charter | .1 Expert judgement | .1 Requirements documentation | Project Scope Management |
|  | .2 Project management plan - Scope management plan - Requirements management plan - Stakeholder engagement plan | .2 Data gathering - Brainstorming - Interviews - Focus groups - Questionnaires and surveys - Benchmarking | .2 Requirements traceability matrix |  |
|  | .3 Project documents - Assumption log - Lessons learned register - Stakeholder register | .3 Data analysis - Document analysis |  |  |
|  | .4 Business documents - Business case | .4 Decision making - Voting - Multicriteria decision analysis |  |  |
|  | .5 Agreements | .5 Data representation - Affinity diagrams - Mind mapping |  |  |
|  | .6 Enterprise environmental factors | .6 Interpersonal and team skills |  |  |
|  | .7 Organizational process assets | .7 Context diagram |  |  |
|  |  | .8 Prototypes |  |  |

| Scope Planning Process – Define Scope #5.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Define Scope | .1 Project charter | .1 Expert judgment | .1 Project scope statement | Project Scope Management |
|  | .2 Project management plan - Scope management plan | .2 Data analysis - Alternatives analysis | .2 Project documents updates - Assumption log - Requirements documentation - Requirements traceability matrix - Stakeholder register |  |
|  | 3. Project documents - Assumption log - Requirements documentation - Risk register | .3 Decision making - Multicriteria decision analysis |  |  |
|  | .4 Enterprise environmental factors | .4 Interpersonal and team skills |  |  |
|  | .5 Organizational process assets | .4 Product analysis |  |  |

| Scope Planning Process – Create WBS #5.4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING |  | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name |  | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Create WBS |  | .1 Project management plan - Scope management plan | .1 Expert judgement | .1 Scope baseline | Project Scope Management |
|  |  | .2 Project documents - Project scope statement - Requirements documentation | .2 Decomposition | .2 Project documents updates - Assumption log - Requirements documentation |  |
|  |  | .3 Enterprise environmental factors |  |  |  |
|  |  | .4 Organizational process assets |  |  |  |

| Scope Planning Process – Validate Scope #5.5 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING |  | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name |  | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Validate Scope |  | .1 Project management plan - Scope management plan - Requirements management plan - Scope baseline | .1 Inspection | .1 Accepted deliverables | Project Scope Management |
|  |  | .2 Project documents - Lessons learned register - Quality reports - Requirements documentation - Requirements traceability matrix | .2 Decision making - Voting | .2 Work performance information |  |
|  |  | .3 Verified deliverables |  | .3 Change requests |  |
|  |  | .4 Work performance data |  | .4 Project documents updates - Lessons learned register - Requirements documentation - Requirements traceability matrix |  |

| Scope Monitor & Control Process – Control Scope #5.6 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Scope | .1 Project management plan - Scope management plan - Requirements management plan - Configuration management plan - Scope baseline - Performance measurement baseline | .1 Data analysis - Variance analysis - Trend analysis | .1 Work performance information | Project Scope Management |
|  | .2 Project documents - Lessons learned register - Requirements documentation - Requirements traceability matrix |  | .2 Change requests |  |
|  | .3 Work performance data |  | .3 Project management plan updates - Scope management plan - Scope baseline - Schedule baseline - Cost baseline - Performance measurement baseline |  |
|  | .4 Organizational process assets |  | .4 Project documents updates - Lessons learned register - Requirements documentation - Requirements traceability matrix |  |

| Schedule Planning Process – Plan Schedule Management #6.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Schedule Management | .1 Project charter | .1 Expert judgment | .1 Schedule management plan | Project Schedule Management |
|  | .2 Project management plan - Scope management plan - Development approach | .2 Data analysis |  |  |
|  | .3 Enterprise environmental factors | .3 Meetings |  |  |
|  | .4 Organizational process assets |  |  |  |

| Schedule Planning Process – Define Activities #6.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Define Activities | .1 Project management plan - Schedule management plan - Scope baseline | .1 Expert judgment | .1 Activity list | Project Schedule Management |
|  | .2 Enterprise environmental factors | .2 Decomposition | .2 Activity attributes |  |
|  | .3 Organizational process assets | .3 Rolling wave planning | .3 Milestone list |  |
|  |  | .4 Meetings | .4 Change requests |  |
|  |  |  | .5 Project management plan updates - Schedule baseline - Cost baseline |  |

| Schedule Planning Process – Sequence Activities #6.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING |  | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name |  | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Sequence Activities |  | .1 Project management plan - Schedule management plan - Scope baseline | .1 Precedence diagramming method | .1 Project schedule network diagrams | Project Schedule Management |
|  |  | .2 Project documents - Activity attributes - Activity list - Assumption log - Milestone list | .2 Dependency determination and integration | .2 Project document updates - Activity attributes - Activity list - Assumption log - Milestone list |  |
|  |  | .3 Enterprise environmental factors | .3 Leads and lags |  |  |
|  |  | .4 Organizational process assets | .4 Project management information system |  |  |

| Schedule Planning Process – Estimate Activity Durations #6.4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Estimate Activity Durations | .1 Project management plan - Schedule management plan - Scope baseline | .1 Expert judgement | .1 Duration estimates | Project Schedule Management |
|  | .2 Project documents - Activity attributes - Activity list - Assumption log - Lessons learned register - Milestone list - Project team assignments - Resource breakdown structure - Resource calendars - Resource requirements - Risk register | .2 Analogous estimating | .2 Basis of estimates |  |
|  | .3 Enterprise environmental factors | .3 Parametric estimating | .. Project document updates - Activity attributes - Assumption log - Lessons learned register |  |
|  | .4 Organizational process assets | .4 Three-point estimating |  |  |
|  |  | .5 Bottom-up estimating |  |  |
|  |  | .6 Data analysis - Alternatives analysis - Reserve analysis |  |  |
|  |  | .7 Decision making |  |  |
|  |  | .8 Meetings |  |  |

| Schedule Planning Process – Develop Schedule #6.5 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Develop Schedule | .1 Project management plan - Schedule management plan - Scope baseline | .1 Schedule network analysis | .1 Schedule baseline | Project Schedule Management |
|  | .2 Project documents - Activity attributes - Activity list - Assumption log - Basis of estimates - Duration estimates - Lessons learned register - Milestone list - Project schedule network diagrams - Project team assignments - Resource calendars - Resource requirements - Risk register | .2 Critical path method | .2 Project schedule |  |
|  | .3 Agreements | .3 Resource optimization | .3 Schedule data |  |
|  | .4 Enterprise environmental factors | .4 Data analysis - What-if scenario analysis - Simulation | .4 Project calendars |  |
|  | .5 Organizational process assets | .5 Leads and lags | .5 Change requests |  |
|  |  | .6 Schedule compression | .6 Project management plan updates - Schedule management plan - Cost baseline |  |
|  |  | .7 Project management information system | .7 Project document updates - Activity attributes - Assumption log - Duration estimates - Lessons learned register - Resource requirements - Risk register |  |
|  |  | .8 Agile release planning |  |  |

| Schedule Controlling Process – Control Schedule #6.6 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING |  | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name |  | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Schedule |  | .1 Project management plan - Schedule management plan - Schedule baseline - Scope baseline - Performance measurement baseline | .1 Data analysis - Earned value analysis - Iteration burndown chart - Performance reviews - Trend analysis - What-if scenario analysis | .1 Work performance information | Project Schedule Management |
|  |  | .2 Project documents - Lessons learned register - Project calendars - Project schedule - Resource calendars - Schedule data | .2 Critical path method | .2 Schedule forecasts |  |
|  |  | .3 Work performance data | .3 Project management information system | .3 Change requests |  |
|  |  | .4 Organizational process assets | .4 Resource optimization | .4 Project management plan updates - Schedule management plan - Schedule baseline - Cost baseline - Performance measurement baseline |  |
|  |  |  | .5 Leads and lags | .5 Project document updates - Assumption log - Basis of estimates - Lessons learned register - Project schedule - Resource calendars - Risk register - Schedule data |  |
|  |  |  | .6 Schedule compression |  |  |

| Cost Planning Process – Plan Cost Management #7.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Cost Management | .1 Project charter | .1 Expert judgement | .1 Cost management plan | Project Cost Management |
|  | .2 Project management plan - Schedule management plan - Risk management plan | .2 Data analysis |  |  |
|  | .3 Enterprise environmental factors | .3 Meetings |  |  |
|  | .4 Organizational process assets |  |  |  |

| Cost Planning Process – Estimate Costs #7.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Estimate Costs | .1 Project management plan - Cost management plan - Quality management plan - Scope baseline | .1 Expert judgement | .1 Cost estimates | Project Cost Management |
|  | .2 Project documents - Lessons learned register - Project schedule - Resources requirements - Risk register | .2 Analogous estimating | .2 Basis of estimates |  |
|  | .3 Enterprise environmental factors | .3 Parametric estimating | .3 Project documents updates - Assumption log - Lessons learned register - Risk register |  |
|  | .4 Organizational process assets | .4 Bottom-up estimating |  |  |
|  |  | .5 Three-point estimating |  |  |
|  |  | .6 Data analysis - Alternatives analysis - Reserve analysis - Cost of quality |  |  |
|  |  | .7 Project management information system |  |  |
|  |  | .8 Decision making - Voting |  |  |

| Cost Planning Process – Determine Budget #7.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Determine Budget | .1 Project management plan - Cost management plan - Resource management plan - Scope baseline | .1 Expert judgement | .1 Cost baseline | Project Cost Management |
|  | .2 Project documents - Basis of estimates - Cost estimates - Project schedule - Risk register | .2 Cost aggregation | .2 Project funding requirements |  |
|  | .3 Business documents - Business case - Benefits management plan | .3 Data analysis - Reserve analysis | .3 Project documents updates - Cost estimates - Project schedule - Risk register |  |
|  | .4 Agreements | .4 Historical information review |  |  |
|  | .5 Enterprise environmental factors | .5 Funding limit reconciliation |  |  |
|  | .6 Organizational process assets | .6 Financing |  |  |

| Cost Monitor & Control Process – Control Costs #7.4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INITIATION | PLANNING |  | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name |  | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Costs |  | .1 Project management plan - Cost management plan - Cost baseline - Performance measurement baseline | .1 Expert judgement | .1 Work performance information | Project Cost Management |
|  |  | .2 Project documents - Lessons learned register | .2 Data analysis - Earned value analysis - Trend analysis - Reserve analysis | .2 Cost forecasts |  |
|  |  | .3 Project funding requirements | .3 To-complete performance index | .3 Change requests |  |
|  |  | .4 Work performance data | .4 Project management information system | .4 Project management plan updates - Cost management plan - Cost baseline - Performance measurement baseline |  |
|  |  | .5 Organizational process assets |  | .5 Project document updates - Assumption log - Basis of estimates - Cost estimates - Lessons learned register - Risk register |  |

| Quality Planning Process – Plan Quality Management #8.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Quality Management | .1 Project charter | .1 Expert judgement | .1 Quality management plan | Project Quality Management |
|  | .2 Project management plan - Requirements management plan - Risk management plan - Stakeholder engagement plan - Scope baseline | .2 Data gathering - Benchmarking - Brainstorming - Interviews | .2 Quality metrics |  |
|  | .3 Project documents - Assumptions log - Requirements documentation - Requirements traceability matrix - Risk register - Stakeholder register | .3 Data analysis - Cost-benefit analysis - Cost of quality | .3 Project management plan updates - Risk management plan - Scope baseline |  |
|  | .4 Enterprise environmental factors | .4 Decision making - Multicriteria decision analysis | .4 Project document updates - Lessons learned register - Requirements traceability matrix - Risk register - Stakeholder register |  |
|  | .5 Organizational process assets | .5 Data representation - Flowcharts - Logical data model - Matrix diagrams - Mind mapping |  |  |
|  |  | .6 Test and inspection planning |  |  |
|  |  | .7 Meetings |  |  |

| Quality Planning Process – Manage Quality #8.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Manage Quality | .1 Project management plan - Quality management plan | .1 Data gathering - Checklists | .1 Quality reports | Project Quality Management |
|  | .2 Project documents - Lessons learned register - Quality control measurements - Quality metrics - Risk report | .2 Data analysis - Alternatives analysis - Document analysis - Process analysis - Root cause analysis | .2 Test and evaluation documents |  |
|  | .3 Organizational process assets | .3 Decision making - Multicriteria decision analysis | .3 Change requests |  |
|  |  | .4 Data representation - Affinity diagrams - Cause-and-effect diagrams - Flowcharts - Histograms - Matrix diagrams - Scatter diagrams | .4 Project management plan updates - Quality management plan - Scope baseline - Schedule baseline - Cost baseline |  |
|  |  | .5 Audits | .5 Project documents updates - Issue log - Lessons learned register - Risk register |  |
|  |  | .6 Design for X |  |  |
|  |  | .7 Problem solving |  |  |
|  |  | .8 Quality improvement methods |  |  |

| Quality Monitor & Control Process – Control Quality #8.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Quality | .1 Project management plan - Quality management plan | .1 Data gathering - Checklists - Check sheets - Statistical sampling - Questionnaires and surveys | .1 Quality control measurements | Project Quality Management |
|  | .2 Project documents - Lessons learned register - Quality metrics - Test and evaluation | .2 Data analysis - Performance reviews - Root cause analysis | .2 Verified deliverables |  |
|  | .3 Approved change requests | .3 Inspection | .3 Work performance information |  |
|  | .4 Deliverables | .4 Testing/product evaluations | .4 Change requests |  |
|  | .5 Work performance data | .5 Data representation - Cause-and-effect diagrams - Control charts - Histogram - Scatter diagrams | .5 Project management plan updates - Issue log - Lessons learned register - Risk register - Test and evaluation documents |  |
|  | .6 Enterprise environmental factors | .6 Meetings |  |  |
|  | .7 Organizational process assets |  |  |  |

| Resource Planning Process – Plan Resource Management #9.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Resource Management | .1 Project charter | .1 Expert judgement | .1 Resource management plan | Project Resource Management |
|  | .2 Project management plan - Quality management plan - Scope baseline | .2 Data representations - Hierarchical charts - Responsibility assignment matrix - Test-oriented formats | .2 Team charter |  |
|  | .3 Project documents - Project schedule - Requirements documentation - Risk register | .3 Organizational theory | .3 Project document updates - Assumption log - Risk register |  |
|  | .4 Enterprise environmental factors | .4 Meetings |  |  |
|  | .5 Organizational process assets |  |  |  |

| Resource Planning Process – Estimate Activity Resources #9.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Estimate Activity Resources | .1 Project management plan - Resource management plan - Scope baseline | .1 Expert judgement | .1 Resource requirements | Project Resource Management |
|  | .2 Project documents - Activity attributes - Activity list - Assumption log - Cost estimates - Resource calendars - Risk register | .2 Bottom-up estimating | .2 Basis of estimates |  |
|  | .3 Enterprise environmental factors | .3 Analogous estimating | .3 Resource breakdown structure |  |
|  | .4 Organizational process assets | .4 Parametric estimating | .4 Project document updates - Activity attributes - Assumption log - Lessons learned register |  |
|  |  | .5 Data analysis - Alternatives analysis |  |  |
|  |  | .6 Project management information system |  |  |
|  |  | .7 Meetings |  |  |

| Resource Execution Process – Acquire Resources #9.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Acquire Resources | .1 Project management plan - Resource management plan - Procurement management plan - Cost baseline | .1 Decision making - Multicriteria decision analysis | .1 Physical resource assignments | Project Resource Management |
|  | .2 Project documents - Project schedule - Resource calendars - Resource requirements - Stakeholder register | .2 Interpersonal and team skills - Negotiation | .2 Project team assignments |  |
|  | .3 Enterprise environmental factors | .3 Pre-assignment | .3 Resource calendars |  |
|  | .4 Organizational process assets | .4 Virtual teams | .4 Change requests |  |
|  |  |  | .5 Project management plan updates - Resource management plan - Cost baseline |  |
|  |  |  | .6 Project document updates - Lessons learned register - Project schedule - Resource breakdown structure - Resource requirements - Risk register - Stakeholder register |  |
|  |  |  | .7 Enterprise environmental factors updates |  |
|  |  |  | .8 Organizational process asset updates |  |

| Resource Execution Process – Develop Team #9.4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Develop Team | .1 Project management plan - Resource management plan | .1 Colocation | .1 Team performance assessments | Project Resource Management |
|  | .2 Project documents - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Team charter | .2 Virtual teams | .2 Change requests |  |
|  | .3 Enterprise environmental factors | .3 Communication technology | .3 Project management plan updates - Resource management plan |  |
|  | .4 Organizational process assets | .4 Interpersonal and team skills - Conflict management - Influencing - Motivation - Negotiation - Team building | .4 Project document updates - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Team charter |  |
|  |  | .5 Recognition and rewards | .5 Enterprise environmental factors updates |  |
|  |  | .6 Training | .6 Organizational process asset updates |  |
|  |  | .7 Individual and team assignments |  |  |
|  |  | .8 Meetings |  |  |

| Resource Execution Process – Manage Team #9.5 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Manage Team | .1 Project management plan - Resource management plan | .1 Interpersonal and team skills - Conflict management - Decision making - Emotional intelligence - Influencing - Leadership | .1 Change requests | Project Resource Management |
|  | .2 Project documents - Issue log - Lessons learned register - Project team assignments - Team charter | .2 Project management information system | .2 Project management plan updates - Resource management plan - Schedule baseline - Cost baseline |  |
|  | .3 Work performance reports |  | .3 Project document updates - Issue log - Lessons learned register - Project team assignments |  |
|  | .4 Team performance assessments |  | .4 Enterprise environmental factors updates |  |
|  | .5 Enterprise environmental factors |  |  |  |
|  | .6 Organizational process assets |  |  |  |

| Resource Monitor & Control Process – Control Resources #9.6 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Resources | .1 Project management plan - Resource management plan | .1 Data analysis - Alternatives analysis - Cost-benefit analysis - Performance reviews - Trend analysis | .1 Work performance information | Project Resource Management |
|  | .2 Project documents - Issue log - Lessons learned register - Physical resource assignments - Resource breakdown structure - Risk register | .2 Problem solving | .2 Change requests |  |
|  | .3 Work performance data | .3 Interpersonal and team skills - Negotiating - Influencing | .3 Project management plan updates - Resource management plan - Schedule baseline - Cost baseline |  |
|  | .4 Agreements | .4 Project management information system | .4 Project document updates - Assumption log - Issue log - Lessons learned register - Physical resource assignments - Resource breakdown structure - Risk register |  |
|  | .5 Organizational process assets |  |  |  |

| Communication Planning Process – Plan Communications Management #10.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Communications Management | .1 Project charter | .1 Expert judgement | .1 Communications management plan | Project Communications Management |
|  | .2 Project management plan - Resource management plan - Stakeholder engagement plan | .2 Communications requirements analysis | .2 Project management plan updates - Stakeholder engagement plan |  |
|  | .3 Project documents - Requirements documentation - Stakeholder register | .3 Communication technology | .3 Project document updates - Project schedule - Stakeholder register |  |
|  | .4 Enterprise environmental factors | .4 Communication methods |  |  |
|  | .5 Organizational process assets | .5 Communication methods |  |  |
|  |  | .6 Interpersonal and team skills - Communication styles assessment - Political awareness - Cultural awareness |  |  |
|  |  | .7 Data representation - Stakeholder engagement assessment matrix |  |  |
|  |  | .8 Meetings |  |  |

| Communication Execution Process – Manage Communications #10.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Manage Communications | .1 Project management plan - Resource management plan - Communications management plan - Stakeholder engagement plan | .1 Communication technology | .1 Project communications | Project Communications Management |
|  | .2 Project documents - Change log - Issue log - Lessons learned register - Quality report - Risk report - Stakeholder register | .2 Communications methods | .2 Project management plan updates - Communications management plan - Stakeholder engagement plan |  |
|  | .3 Work performance reports | .3 Communication skills - Communication competence - Feedback - Nonverbal - Presentations | .3 Project document updates - Issue log - Lessons learned register - Project schedule - Risk register - Stakeholder register |  |
|  | .4 Enterprise environmental factors | .4 Project management information system | .4 Organizational process assets updates |  |
|  | .5 Organizational process assets | .5 Project reporting |  |  |
|  |  | .6 Interpersonal and team skills - Active listening - Conflict management - Cultural awareness - Networking - Political awareness |  |  |
|  |  | .7 Meetings |  |  |

| Communication Monitor & Control Process – Monitor Communications #10.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Monitor Communications | .1 Project management plan - Resource management plan - Communications management plan - Stakeholder engagement plan | .1 Expert judgment | .1 Work performance information | Project Communications Management |
|  | .2 Project documents - Issue log - Lessons learned register - Project communications | .2 Project management information system | .2 Change requests |  |
|  | .3 Work performance data | .3 Data analysis - Stakeholder engagement assessment matrix | .3 Project management plan updates - Communications management plan - Stakeholder engagement plan |  |
|  | .4 Enterprise environmental factors | .4 Interpersonal and team skills - Observation/conversation | .4 Project document updates - Issue log - Lessons learned register - Stakeholder register |  |
|  | .5 Organizational process assets | .5 Meetings |  |  |

| Risk Planning Process – Plan Risk Management #11.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Risk Management | .1 Project charter | .1 Expert judgment | .1 Risk management plan | Project Risk Management |
|  | .2 Project management plan - All components | .2 Data analysis - Stakeholder analysis |  |  |
|  | .3 Project documents - Stakeholder register | .3 Meetings |  |  |
|  | .4 Enterprise environmental factors |  |  |  |
|  | .5 Organizational process assets |  |  |  |

| Risk Planning Process – Identify Risks #11.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Identify Risks | .1 Project management plan - Requirements management plan - Schedule management plan - Cost management plan - Quality management plan - Resource management plan - Risk management plan - Scope baseline - Schedule baseline - Cost baseline | .1 Expert judgment | .1 Risk register | Project Risk Management |
|  | .2 Project documents - Assumption log - Cost estimates - Duration estimates - Issue log - Lessons learned register - Requirements documentation - Resource requirements - Stakeholder register | .2 Data gathering - Brainstorming - Checklists - Interviews | .2 Risk report |  |
|  | .3 Agreements | .3 Data analysis - Root cause analysis - Assumption and constraint analysis - SWOT analysis - Document analysis | .3 Project document updates - Assumption log - Issue log - Lessons learned register |  |
|  | .4 Procurement documentation | .4 Interpersonal and team skills - Facilitation |  |  |
|  | .5 Enterprise environmental factors | .5 Prompt lists |  |  |
|  | .6 Organizational process assets | .6 Meetings |  |  |

| Risk Planning Process –Perform Qualitative Risk Analysis #11.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Perform Qualitative Risk Analysis | .1 Project management plan - Risk management plan | .1 Expert judgment | .1 Project document updates - Assumption log - Risk register - Risk report | Project Risk Management |
|  | .2 Project documents - Assumption log - Risk register - Stakeholder register | .2 Data gathering - Interviews |  |  |
|  | .3 Enterprise environmental factors | .3 Data analysis - Risk data quality assessment - Risk probability and impact assessment - Assessment of other risk parameters |  |  |
|  | .4 Organizational process assets | .4 Interpersonal and team skills - Facilitation |  |  |
|  |  | .5 Risk categorization |  |  |
|  |  | .6 Data representation - Probability and impact matrix |  |  |
|  |  | .7 Meetings |  |  |

| Risk Planning Process –Perform Quantitative Risk Analysis #11.4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Perform Quantitative Risk Analysis | .1 Project management plan - Risk management plan - Scope baseline - Schedule baseline - Cost baseline | .1 Expert judgment | .1 Project document updates - Risk report | Project Risk Management |
|  | .2 Project documents - Assumption log - Basis of estimates - Cost estimates - Duration estimates - Milestone list - Resource requirements - Risk register - Risk report - Schedule forecasts | .2 Data gathering - Interviews |  |  |
|  | .3 Enterprise environmental factors | .3 Interpersonal and team skills - Facilitation |  |  |
|  | .4 Organizational process assets | .4 Representations of uncertainty |  |  |
|  |  | .5 Data analysis - Simulations - Sensitivity analysis - Decision tree analysis - Influence diagrams |  |  |

| Risk Planning Process –Plan Risk Responses #11.5 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Risk Responses | .1 Project management plan - Resource management plan - Risk management plan - Cost baseline | .1 Expert judgment | .1 Change requests | Project Risk Management |
|  | .2 Project documents - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Risk register - Risk report - Stakeholder register | .2 Data gathering - Interviews | .2 Project management plan updates - Schedule management plan - Cost management plan - Quality management plan - Resource management plan - Procurement management plan - Scope baseline - Schedule baseline - Cost baseline |  |
|  | .3 Enterprise environmental factors | .3 Interpersonal and team skills - Facilitation | .3 Project document updates - Assumption log - Cost forecasts - Lessons learned register - Project schedule - Project team assignments - Risk register - Risk report |  |
|  | .4 Organizational process assets | .4 Strategies for threats |  |  |
|  |  | .5 Strategies for opportunities |  |  |
|  |  | .6 Contingent response strategies |  |  |
|  |  | .7 Strategies for overall project risk |  |  |
|  |  | .8 Data analysis - Alternatives analysis - Cost-benefit analysis |  |  |
|  |  | .9 Decision making - Multicriteria decision analysis |  |  |

| Risk Execution Process – Implement Risk Responses #11.6 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Implement Risk Responses | .1 Project management plan - Risk management plan | .1 Expert judgment | .1 Change requests | Project Risk Management |
|  | .2 Project documents - Lessons learned register - Risk register - Risk report | .2 Interpersonal and team skills - Influencing | .2 Project document updates - Issue log - Lessons learned register - Project team assignments - Risk register - Risk report |  |
|  | .3 Organizational process assets | .3 Project management information system |  |  |

| Risk Monitor & Control Process – Monitor Risks #11.7 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Monitor Risks | .1 Project management plan - Risk management plan | .1 Data analysis - Technical performance analysis - Reserve analysis | .1 Work performance information | Project Risk Management |
|  | .2 Project documents - Issue log - Lessons learned register - Risk register - Risk report | .2 Audits | .2 Change requests |  |
|  | .3 Work performance data | .3 Meetings | .3 Project management plan updates - Any component |  |
|  | .4 Work performance reports |  | .4 Project document updates - Assumption log - Issue log - Lessons learned register - Risk register - Risk report |  |
|  |  |  | .5 Organizational process assets updates |  |

| Procurement Planning Process – Plan Procurement Management #12.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Procurement Management | .1 Project charter | .1 Expert judgement | .1 Procurement management plan | Project Procurement Management |
|  | .2 Business documents - Business Case - Benefits management plan | .2 Data gathering - Market research | .2 Procurement strategy |  |
|  | .3 Project management plan - Scope management plan - Quality management plan - Resource management plan - Scope baseline | .3 Data analysis - Make-or-buy analysis | .3 Bid documents |  |
|  | .4 Project documents - Milestone list - Project team assignments - Requirements documentation - Requirements traceability matrix - Resource requirements - Risk register - Stakeholder register | .4 Source selection analysis | .4 Procurement statement of work |  |
|  | .5 Enterprise environmental factors | .5 Meetings | .5 Source selection criteria |  |
|  | .6 Organizational process assets |  | .6 Make-or-buy decisions |  |
|  |  |  | .7 Independent cost estimates |  |
|  |  |  | .8 Change requests |  |
|  |  |  | .9 Project document updates - Lessons learned register - Milestone list - Requirements documentation - Requirements traceability matrix - Risk register - Stakeholder register |  |
|  |  |  | .10 Organizational process assets updates |  |

| Procurement Execution Process – Conduct Procurements #12.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Conduct Procurements | .1 Project management plan - Scope management plan - Communications management plan - Risk management plan - Procurement management plan - Configuration management plan - Cost baseline | .1 Expert judgement | .1 Selected sellers | Project Procurement Management |
|  | .2 Business documents - Lessons learned register - Project schedule - Requirements documentation - Risk register - Stakeholder register | .2 Advertising | .2 Agreements |  |
|  | .3 Procurement documentation | .3 Bidder conferences | .3 Change requests |  |
|  | .4 Seller proposals | .4 Data analysis - Proposal evaluation | .4 Project management plan updates - Requirements management plan - Quality management plan - Communications management plan - Risk management plan - Procurement management plan - Scope baseline - Schedule baseline - Cost baseline |  |
|  | .5 Enterprise environmental factors | .5 Interpersonal and team skills - Negotiation | .5 Project documents updates - Lessons learned register - Requirements documentation - Requirements traceability matrix - Resource calendars - Risk register - Stakeholder register |  |
|  | .6 Organizational process assets |  | .6 Organizational process assets updates |  |

| Procurement Monitor & Control Process – Control Procurements #12.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Control Procurements | .1 Project management plan - Requirements management plan - Risk management plan - Procurement management plan - Change management plan - Schedule baseline | .1 Expert judgement | .1 Closed procurements | Project Procurement Management |
|  | .2 Project documents - Assumption log - Lessons learned register - Milestone list - Quality reports - Requirements traceability matrix - Risk register - Stakeholder register | .2 Claims administration | .2 Work performance information |  |
|  | .3 Agreements | .3 Data analysis - Performance reviews - Earned value analysis - Trend analysis | .3 Procurement documentation updates |  |
|  | .4 Procurement documentation | .4 Inspection | .4 Change requests |  |
|  | .5 Approved change requests | .5 Audits | .5 Project management plan updates - Risk management plan - Procurement management plan - Schedule baseline - Cost baseline |  |
|  | .6 Work performance data |  | .6 Project document updates - Lessons learned register - Resource requirements - Requirements traceability matrix - Risk register - Stakeholder register |  |
|  | .7 Enterprise environmental factors |  | .7 Organizational process assets updates |  |
|  | .8 Organizational process assets |  |  |  |

| Stakeholder Initiating Process – Identify Stakeholders #13.1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Identify Stakeholders | .1 Project charter | .1 Expert judgment | .1 Stakeholder register | Project Stakeholder Management |
|  | .2 Procurement documents - Business case - Benefits management plan | .2 Data gathering - Questionnaires and surveys - Brainstorming | .2 Change requests |  |
|  | .3 Project management plan - Communications management plan - Stakeholder engagement | .3 Data analysis - Stakeholder analysis - Document analysis | .3 Project management plan updates - Requirements management plan - Communications management plan - Risk management plan - Stakeholder engagement plan |  |
|  | .4 Project documents - Change log - Issue log - Requirements documentation | .4 Data representation - Stakeholder mapping/ representation | 4. Project document updates - Assumption log - Issue log - Risk register |  |
|  | .5 Agreements | .5 Meetings |  |  |
|  | .6 Enterprise environmental factors |  |  |  |
|  | .7 Organizational process assets |  |  |  |

| Stakeholder Planning Process – Plan Stakeholder Engagement #13.2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Plan Stakeholder Engagement | .1 Project charter | .1 Expert judgment | .1 Stakeholder management plan | Project Stakeholder Management |
|  | .2 Project management plan - Resource management plan - Communications management plan - Risk management plan | .2 Data gathering - Benchmarking |  |  |
|  | .3 Project documents - Assumption log - Change log - Issue log - Project schedule - Risk register - Stakeholder register | .3 Data analysis - Assumption and constraint analysis - Root cause analysis |  |  |
|  | .4 Agreements | .4 Decision making - Prioritization/ranking |  |  |
|  | .5 Enterprise environmental factors | .5 Data representation - Mind mapping - Stakeholder engagement assignment matrix |  |  |
|  | .6 Organizational process assets | .6 Meetings |  |  |

| Stakeholder Execution Process – Manage Stakeholder Engagement #13.3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Manage Stakeholder Engagement | .1 Project management plan - Communications management plan - Risk management plan - Stakeholder engagement plan - Change management plan | .1 Expert judgment | .1 Change requests | Project Stakeholder Management |
|  | .2 Project documents - Change log - Issue log - Lessons learned register - Stakeholder register | .2 Communication skills - Feedback | .2 Project management plan updates - Communication management plan - Stakeholder engagement plan |  |
|  | .3 Enterprise environmental factors | .3 Interpersonal and team skills - Conflict management - Cultural awareness - Negotiation - Observation/conversation - Political awareness | .3 Project documents updates - Change log - Issue log - Lessons learned register - Stakeholder register |  |
|  | .4 Organizational process assets | .4 Ground rules |  |  |
|  |  | .5 Meetings |  |  |

| Stakeholder Monitor & Control Process – Monitor Stakeholder Engagement #13.4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| INITIATION | PLANNING | EXECUTION | MONITOR & CONTROL | CLOSING |
| Process name | Inputs | Tools and techniques | Outputs | Knowledge Area |
| Monitor Stakeholder Engagement | .1 Project management plan - Resource management plan - Communications management plan - Stakeholder engagement plan | .1 Data analysis - Alternatives analysis - Root cause analysis - Stakeholder analysis | .1 Work performance information | Project Stakeholder Management |
|  | .2 Project documents - Issue log - Lessons learned register - Project communications - Risk register - Stakeholder register | .2 Decision making - Multicriteria decision analysis - Voting | .2 Change requests |  |
|  | .3 Work performance data | .3 Data representation - Stakeholder engagement assessment matrix | .3 Project management plan updates - Resource management plan - Communications management plan - Stakeholder engagement plan |  |
|  | .4 Enterprise environmental factors | .4 Communication skills - Feedback - Presentations | .4 Project documents updates - Issue log - Lessons learned register - Risk register - Stakeholder register |  |
|  | .5 Organizational process assets | .5 Interpersonal and team skills - Active listening - Cultural awareness - Leadership - Networking - Political awareness |  |  |
|  |  | .6 Meetings |  |  |